## Slide 1: County-wide Shared Services Initiative
Jason Molino
County Administrator
April 25, 2019

## Slide 2: Agenda
Overview of 2018 Plan
  Results
  Successes
  Challenges
2020 Initiative Action Plan
  Requirements
  Timeline
  Next steps

## Slide 3: 2018 Plan Results
Plan Projects
  Tompkins County recommended six (6) projects for implementation in the 2018 plan submitted to NYS.
  The following shared service projects were completed and deemed successful:
      Tompkins County Council of Governments (TCCOG) Training Academy
      Service Modernization Plan (Laserfiche)
      County-wide Mass Notification System (Swift911)
      Greater Tompkins County Municipal Health Insurance Consortium (GTCMHIC)
Matchable Savings
  The submitted shared service projects between municipalities resulted in a potential Certified Matchable Savings of $385,679.93.
  Our application is currently under review and awaiting acceptance from NYS.

## Slide 4: 2018 Plan Successes
Tompkins County was one (1) of thirty-four (34) counties to submit a shared services plan during the first year the initiative was mandated.
Tompkins County has been a pioneer in shared services allowing the County to be ahead in the process.
Completed application and documentation was submitted to the Department of State within allowable timeframe and is currently under review for a potential fund matches.

## Slide 5: 2018 Plan Challenges
Difficulty identifying potential shared service opportunities that would result in high dollar savings
      Tompkins County has already developed many shared service projects in past years limiting additional opportunities. For example: Public Transit, Solid Waste/Recycling, Community College, Assessment, Civil Service
Anticipated projects that were not implemented within the 2018 calendar year for implementation
      LED Street Lights
      IT Purchasing Pool
Communication
      At times it took several outreach attempts for County Administration to receive responses or documentation from participating municipalities

## Slide 6: 2020 Plan Requirements
Panel Convened
      Required Participants: County Administrator, Mayors of every city and village, Supervisors of every town within the County.
      Optional Participants: School districts, BOCES, fire districts, fire protection districts
Plan recommendations must be considered from all Panel members as well as the representative of each collective bargaining unit of the county and the cities, towns, and villages and other optional invited panel members.
Minimum of two (2) panel meetings
Finalize plan submitted to Legislature for review and recommendations
      Legislature can modify the plan and issue recommendations, but cannot reject the plan submitted to them
3 public hearings (Public is encouraged to contribute ideas)
Panel majority vote to approve plan (If approved, to be implemented the following year)
Public presentation of plan
Plan must be submitted by end of 2019

## Slide 7: 2020 Plan Timeline
April 25, 2019
By October 30, 2019
By August 1, 2019
By September 30, 2019
County Administrator consults with panel, collective bargaining units, and stakeholders
Minimum of three (3) public hearings held within the County
Panel develops plan draft
County Administrator submits plan and certification of savings to Legislature for review and comment
Panel is created and convened
Legislature provides recommendations to the plan
Panel votes on final plan
County Administrator submits plan to Secretary of State with savings certified
County Administrator publicly disseminates plan
County Administrator conducts public presentation of Plan after public notice

## Slide 8: Next Steps
      Panel meetings
        May 23rd 4:30p.m.
        June 27th 4:30p.m.
        July 25th 4:30p.m.
      Extend invitations to collective bargaining units and other optional panel members
      Identify potential shared service opportunities
      Estimate potential savings
      Schedule public hearings
        June ? and June 27th
        July 25th
      Draft plan complete for submission to Legislature